## Sheet1
OUTLINE ACTION/WORK PLAN FOR THE THEnet SOCIAL ACCOUNTABILITY FRAMEWORK FOR HEALTH WORKFORCE TRAINING
|  |  |  | THEnet tools for use at each stage | Who | [6 empty] | When (current year)
Activity or Deliverable |  |  |  |  | School | School | School | School | School | School | School | month | month | month | month | month | month | month
Preparation
Prior to Starting School Process
Budget preparation and securing budgetary support
Secure administrative/research/school support staff (team)
Please add any further processes in here...
Please add any further processes in here...
Step 1: Ethics application
Workshop with faculty, staff and community members
Create and submit ethics application
| Create ethics applications |  |  | Generic ethics application
Please add any further processes in here...
Please add any further processes in here...
Step 2: Promotion of Framework and identification of available document/data collection
Workshop with faculty, staff and community members
School Processes
Decide which faculty, staff, and community members need to be invited
Invite members using options of phone, email and official letter
| Prepare for workshop (using the workbook and PowerPoint presentation provided by THEnet) |  |  | Workshop Workbook
| Have workshop to foster relationships and identify the location and ownership of documentation evidence |  |  | Workshop PowerPoint Presentation
Collate workshop results
Thank attendees using options of phone, email and official letter
Contact owners of documentary evidence to see if they do own the evidence, let them know of the workshop outcome and that you would soon like access to the documents
Please add any further processes in here...
Please add any further processes in here...
Step 3: Collect data
Interviews/Focus Groups with faculty, staff and community members
School Processes
Identify community members, students and staff to interview/focus group
| Modify the interview/focus group questions for local context, including translation if required |  |  | List of SA focus group / interview questions
Invite community members, students and staff using options of phone, email and official letter
Prepare and print required consent forms and questions (from your schools approved ethics application)
| Prepare recording device by checking batteries plus amount of space left on the device for recording |  |  | Guide for conducting focus groups / interviews
Undertake interviews/focus groups as required (use an external facilitator to your school is possible)
Immediately after each interview/focus group, write down your reflections of responses, and potential themes you see emerging from each question.
Please add any further processes in here...
Please add any further processes in here...
Data and Document collection (matched to the framework)
School Processes
Contact the people who were identified as holders of data/documentation during the workshop
Request a copy of the data/documentation (electronically if possible)
Record data/documents collected in one folder
Identify missing data/documents for each indicator, assess if school has the data source, and collect if possible
Please add any further processes in here...
Please add any further processes in here...
Step 4: Reflection and Analysis of data
Reflection on, and analysis of interviews/focus groups
Reflect on all interviews/focus groups using a software package (such as NVivo) or traditionally thematically code your data using your critical analysis of the discussion
Create any tables as required for the interview/focus group results for both theme analysis and the report
If possible, 'verify' data results with an external person familiar with qualitative tecniques (or the administrator of your school)
Please add any further processes in here...
Please add any further processes in here...
Reflection on, and analysis of data/documents collected
Reflect on all data/documentation collected, and collate what has been collected against each indicator
Critical and creative reflection of documents and data against the indicators will assist with identifying themes, strengths and recommendations
Please add any further processes in here...
Please add any further processes in here...
Step 5: Report Writing
Synthesising and Collating Data (by focussing on the indicators)
School Processes
Write up your critical assessment of the schools performance, progress, knowledge and skills towards social accountability
The report should identify any strengths, weaknesses, and gaps, and identify recommendations to any gaps
Please add any further processes in here...
Please add any further processes in here...
Step 4: Result Dissemination
Please add any further processes in here...
Please add any further processes in here...
Other
In-person meeting
Regular SKYPE-in calls
Notes:
| P | Process has been achieved
Process is to be achieved